Cooperative Development of Operational Safety and Continuing Airworthiness

# Under ICAO Technical Co-operation Programme

# COSCAP-South Asia

13th STEERING COMMITTEE MEETING

DP 6   FUNDING AND BUDGET

Discussion Paper

1.	Introduction

1.1	The purpose of this paper is to provide Steering Committee Members with an 	update 	of the funding received since the last Steering Committee Meeting and to provide a 	Budget update for the Programme for 2005.

2. 	Funding

2.1	Contributions since the 12th COSCAP-SA Steering Committee Meeting have 	been received as follows:

(a)	Bangladesh	-  $29,990

(b)	Bhutan		-

(c)	India		-  $100,346 (contribution received in December 2003 for 			    	    the year 2003)

(d)	Maldives	-  $19,990

(e)	Nepal		-

(f)	Pakistan	-  $29,965

(g)	Sri Lanka	-  $48,590

(h)	EC		-

(i)	Airbus		-

(j)	Boeing		-

2.2	Details on SMS Expert.  A Safety Management Systems Expert, who previously 	provided training and technical assistance in CRM for three months (October – December 	2003), was further engaged to provide training and technical assistance in the area of 	SMS.  The Expert conducted a five-day SMS Course for Operations and Airworthiness 	personnel in all seven States and also provided technical assistance on SMS matters 	during the follow-up visits.  Travel within the region was facilitated by the respective 	Directors General.

2.3	Details on ATS Expert. Partial funding received from Boeing permitted 	engagement of an Air Traffic Services Expert for 10 weeks starting 19 January 2004. The 	Expert provided a total of 45 days of technical assistance in all seven States to prepare for

the ICAO Universal Safety Oversight Audit. Travel within the region was facilitated by the respective Directors General.

2.4	Details on ACST Expert.  An Aerodrome Certification and Safety Training Expert was engaged for four months starting 28 January 2004.  The Expert provided 66 days of technical assistance in all seven Member States to assist States with their initial preparation for the ICAO Universal Safety Oversight Audit.  Travel within the region was facilitated by the respective Directors General.

2.5	Details on DG Safety Oversight Workshop.  Full funding received from Boeing enabled the three COSCAP Programmes in Asia to collectively arrange a five-day 	 Dangerous Goods Safety Oversight Workshop conducted under the aegis of ICAO at the Regional Office.

2.6	Details on Aviation Medicine Workshop.  COSCAP-SA funds were utilized to engage an Aviation Medicine Expert for 14 days to conduct a three-day workshop at two locations.  Air transportation was provided by DGCA India.

2.7	Details on Cabin Safety Workshop.  Partial funding received from Boeing and in-kind support from the International Society of Air Safety Investigators (ISASI) permitted engagement of two Cabin Safety Experts for 15 days to conduct a five-day course/workshop at two locations.  Air transportation was provided by DGCA India and CAA Pakistan.

2.8	Appendix I reflects the total funds received by ICAO for the Project as of 1 September 2004.  The contracts of the Project Coordinator/Regional Flight Operations Expert and the Regional Airworthiness Inspector are through the end of March 2005, but can be extended through the 1st week of June 2005 because of available funds.  The contracts may be further extended subject to receipt of additional funds from Member States and Donors. The positions of the Regional Aerodrome Expert and the Regional ATS Expert could not be filled because of insufficient funds.

3. 	Budget

3.1	Appendix II outlines the latest budget based on the funds available as of 1 September 2004, which is expected to permit the operation of the programme up to approximately the 1st week of June 2005, with One Project Coordinator/Regional Flight Operations Expert and One Regional Airworthiness Inspector.

4.  	Action by the Meeting

4.1	Approval of the programme Budget at Appendix II for 2005.

APPENDIX I

COSCAP-SA PROJECT FUNDING

(As on 23 November 2004)

STATE CONTRIBUTION

| S.N | STATE | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Bangladesh | - | 29940 | 24990 | 28067 | 29975 | 29958 | 29990 | 29990 | 202,910 |
| 2. | Bhutan | 9780 | 9653 | 6896 | 3279 | 3269 | 9975 | 9975 |  | 52,827 |
| 3. | India | - | 74965 | 112433 | 59965 | 63321 | 113999 | 100346 |  | 525,029 |
| 4. | Maldives | 15990 | 19990 | 19990 | 19990 | 19990 | 19990 | 19990 | 19990 | 155,920 |
| 5. | Nepal | 30000 | 10000 | 19990 | 29913 | 19958 | 29990 | - |  | 139,851 |
| 6. | Pakistan | - | 25000 | - | 70988 | - | 94508 | 47624 | 29,965 | 268,085 |
| 7. | Sri Lanka | - | 20000 | 25000 | 25000 | 50000 | 49366 | 50000 | 48590 | 267,956 |
|  | TOTAL: | 55770 | 189548 | 209299 | 237202 | 186513 | 347786 | 257925 | 128,535 | 1,582,588 |

# DONOR CONTRIBUTION

|  | DONOR | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Airbus | 100000 | 49990 | 49990 | 49990 | 49990 | 50000 | - |  | 349,960 |
| 2. | Boeing1 | - | - | - | - | 50000 | 50000 | 50000 |  | 150,000 |
| 3. | Canada | - | 134117 | 68027 | 66666 | - | 62893 | - |  | 331,703 |
| 4. | FAA | 60000 | 85000 | - | - | - | - | - |  | 145,000 |
|  | TOTAL: | 160000 | 269107 | 118017 | 116656 | 99990 | 162893 | 50000 |  | 976,663 |

# NORAD CONTRIBUTION

| 1. | Norway2 Less: Refund of Contribu-tion Balance | - | 240610 - 240610 | 202235 - 202235 | 190625 120170 70455 | 108824 132342 (23518) |  |  |  | 489,782 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

EUROPEAN CONTRIBUTION

| 1. | European Commis-sion3 | - | - | - | - | 213681 | 75292 |  |  | 288,973 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# BANK INTEREST

|  |  | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | State+Donor | 3791 | 19431 | 26788 | 34393 | 21514 | 8342 | 6013 | 4296 | 124,568 |
| 2. | Norway | - | 1552 | 4507 | 6080 | 2496 | - |  |  | 14,635 |
| 3. | EC | - | - | - | - | 2428 | 3276 |  | 47 | 5,751 |
|  | TOTAL: | 3791 | 20983 | 31295 | 40473 | 26438 | 11618 | 6013 | 4343 | 144,954 |

|  |  | TOTAL PROJECT FUNDS: US $ 3,429,383 |
| --- | --- | --- |

Notes:

1.      Boeing Contribution tied to specific activities agreed between Boeing and Project.

2.      Norway Contribution was tied to the recruitment of the International Airworthiness Expert.  This has been completed and  the post is therefore no longer reflected in Appendices II and III.

- EC Contribution is tied to specific inputs identified in EC/ICAO Grant Agreement.

TOTAL RAS/97/902		US$2,630,242*

TOTAL RAS/97/906 (NORAD)	US$   504,417

TOTAL RAS/00/802 – EC SA	US$   294,724

TOTAL                                        US$3,429,383

*Total RAS/97/902 was reduced to reflect decrease of EC contribution by US$83,567.

|  | DONOR CONTRIBUTION IN KIND |  |  |
| --- | --- | --- | --- |
|  | 1. FAA: Dangerous Goods Courses / SARAST | 60,000 |  |
|  | Transport Canada: Cabin Safety/TA/CPC/WLH/Computers/AVN SEC/Cabin Safety/ Aviation Enforcement | 166,000 |  |
|  | 3. Airbus Industrie: ETOPS/Cat II and III /Lic./MMEL/ A310 Type Rating/NDT/SIM | 140,190 |  |
|  | 4. JAA: Licensing Courses | 15,000 |  |
|  | 5. Boeing Company: Safety Promotion/Perf. Review/Accident Prevention/GPS/MEDA/Structure | 70,000 |  |
|  | 6. JAA : JAR 145 Course | 10,000 |  |
|  | 7. Nepal (establishing of COSCAP Office for 7 yrs) 8. Maldives - GPS Workshops | 63,000 18,000 |  |
|  | TOTAL |  | 542,190 |

State's Contribution of Air Transportation in Kind

(December 2000 to November 2004)

| Bangladesh (Biman) | $ 9,170 |
| --- | --- |
| Bhutan (Druk) | $ 6,739 |
| India (Indian Airlines + Air India) | $ 13,990 |
| Maldives (Sri Lankan) | $ 7,034 |
| Nepal (RNAC) | $ 7,320 |
| Pakistan (PIA) | $ 9,595 |
| Sri Lanka (Sri Lankan) | $ 26,524 |
| Total: | $ 80,372 |

Click here for Appendix II - BUDGET